## Sheet1
Stakeholder Analysis
Stakeholder | Their interest | What the project needs from them | Perceived attitudes and/or risks | Actions to take
ITI | Well educated trainee | Funds | Being late | Raise money from ourselves
Instructors | Deliver information to prepare qualified employees to the market | Supporting with the enough information and well delivering for the software engineering science
customers from the community | Getting an efficient application with the minimum price | Their feedbacks
H/W supplier | Gaining money | all needed hardware to be available | There's no any risk
S/W supplier (Us) | Gaining and gathering information about software engineering science | Having a good background in coding and implementing hardware | There's no any risk
Project Scope |  |  |  |  | Temprature Range | Fan Speed
Designing an automatic fan controller system that allow the user to read the current temprature and the fan speed through LCD, the system contatin a temprature sensor to detect the current temprature and change the fan speed according to it automatically. there are only three possible fan speed as shown in the next table. if the temprature is less than 15 degree, the system will consider it as speed one and if the temprature is more than 30 degree, the system will consider it as speed three. There will not be any other user interface and there is no a manual user mode. the used microconntroller is from AVR family only. This project is to be delivered in five weeks starting from March 5th to April 9th, 2016. |  |  |  |  | 15 to 20 | Speed1
[5 empty] | 20 to 25 | Speed2
[5 empty] | 25 to 30 | Speed3
Roles and Responsibilities
Project Sponsor (ITI) |  | Providing approval for any issues requiring additional time or scope
Project Manager (Kareem) |  | Overall management
Identification of CIs
Providing configuration standards and templates to the project team
Ensuring that the Project Team completes the project
Providing any required configuration training
Team Members |  | Designating a focus group to develop the change request
Ensure all change requests comply with organizational templates
Working on project tasks, change requests and review each other's work
Objectives
List of Objectives | Away to measure
Power Efficiency | test the battery life time
Efficient use of resources | Test if all resources are well used without wasting
Reliable system | Test the system in different environments to ensure its reliability
Modularity | Ensuring the system is devided to independent modules and is well commented
Configurability | Ensuring the system is applicable in different users configurations