## Sheet1
RISK SHEET
Step 1: Risk Identification | Step 2: Risk Assessment |  | Step 3: Risk Management
List of Possible Risks | Likelihood | Impact | What are we already doing about it? (mitigating factors) | Person Responsible
One of the technical staff had an emergency. | Medium | High | Assign for evey member a backup person to do his/her task | Team Manager
Financial issue to get the components and the project tools. | Low | High | contact frequantly with the customer and insure the financial supply on the time | Project Manager
The Product didn't meet the requirements of the customer in the delivery phase. | Medium | High | Periodically Review with the customer every phase that the product meet his requirements | Project Manager
Damage happened with the project components or tools in the development phase | High | High | Buy a backup component for the components that have a High risk to be damaged and set it in the financial plan | Project Manager
Delay in delivery the tasks during the development pahse | High | High | Make a safety factor in the time scheduler | Team Manager