## Schedule
Project Schedule
| Project Name: | FAN CONTROLLER SYSTEM
| Project Manager Name: | Kareem Galal
| Project Start Date: | March 5th, 2016
| Project Schedule Last Updated Date: | 2016-04-08 21:24
ID | Task Name | Duration |  | Status | Expected Start | Actual Start | Expected Finish | Actual Finish | EAC |  | Actual Work |  | % Complete | Predecessors | Resource Names
0 | Project Schedule | 35 | days | Current | 2016-03-05 | 2016-03-06 | 2016-04-09 | NA | 70 | hrs | 73 | hrs | 96.43% |  | Kareem Galal
0 | Review Log Sheet | 28 | days | Current | 2016-03-12 | 2016-03-14 | 2016-04-09 | NA | 2 | hrs | 2 | hrs | 100% |  | Tarek & Hassan
1 | Project Management | 7 | days | done | 2016-03-05 | 2016-03-05 | 2016-03-11 | 2016-03-11 | 10 | hrs | 14 | hrs | 100%
1.1 | Project Management Plan | 7 | days | done | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-16 | 4 | hrs | 8 | hrs | 100% |  | Hoda & Mariam
1.2 | Estimation Sheet | 7 | days | done | 2016-03-05 | 2016-03-07 | 2016-03-11 | 2016-03-11 | 2 | hrs | 2 | hrs | 100% |  | Hassan
1.3 | Risk Sheet | 2 | days | done | 2016-03-05 | 2016-03-08 | 2016-03-11 | 2016-03-10 | 2 | hrs | 2 | hrs | 100% |  | Tarek
1.4 | CI list (Folder Structure) | 2 | days | done | 2016-03-05 | 2016-03-08 | 2016-03-11 | 2016-03-10 | 2 | hrs | 2 | hrs | 100% |  | Yasser
2 | Requirements & Test Plans | 7 | days | done | 2016-03-12 | 2016-03-12 | 2016-03-18 | 2016-04-01 | 12 | hrs | 16 | hrs | 100% | 1
2.1 | CRS-SIQ | 2 | days | done | 2016-03-12 | 2016-03-12 | 2016-03-14 | 2016-03-16 | 2 | hrs | 4 | hrs | 100% |  | Yasser & Mariam
2.2 | SRS | 2 | days | done | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-29 | 4 | hrs | 6 | hrs | 100% | 2.1 | Kareem & Hassan then Kareem & Tarek
2.3 | RTM(Just SRS >> CRS) | 2 | days | done | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-29 | 4 | hrs | 4 | hrs | 100% | 2.1 & 2.2 | Kareem & Hassan then Kareem
2.4 | Test cases | 2 | days | done | 2016-03-18 | 2016-03-29 | 2016-03-20 | 2016-04-01 | 2 | hrs | 2 | hrs | 100% | 2.2 | Mariam
3 | Design & Code | 14 | days | done | 2016-03-19 | 2016-03-19 | 2016-04-01 | 2016-04-02 | 22 | hrs | 22 | hrs | 100% | 2
3.1 | HLD | 4 | days | done | 2016-03-19 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 4 | hrs | 4 | hrs | 100% |  | Hassan
3.2 | CDDs | 4 | days | done | 2016-03-23 | 2016-03-24 | 2016-03-27 | 2016-04-02 | 6 | hrs | 6 | hrs | 100% | 3.1 | Mariam & Hoda & Hassan
3.3 | Update RTM with Design | 1 | days | done | 2016-03-27 | 2016-04-02 | 2016-03-27 | 2016-04-01 | 2 | hrs | 2 | hrs | 100% | 3.2 | Kareem
3.4 | Code Implementation | 2 | days | done | 2016-03-27 | 2016-03-24 | 2016-03-29 | 2016-04-01 | 6 | hrs | 6 | hrs | 100% | 3.2 | Tareek & Yasser
3.5 | Update RTM with Code | 1 | days | done | 2016-03-29 | 2016-04-01 | 2016-03-29 | 2016-04-02 | 2 | hrs | 2 | hrs | 100% | 3.4 | Kareem
3.6 | Hardware purchasing | 2 | days | Done | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2 | hrs | 2 | hrs | 100% |  | Tareek
4 | Testing | 7 | days | current | 2016-04-02 | 2016-04-03 | 2016-04-09 | NA | 24 | hrs | 19 | hrs | 85.71%
4.1 | Update SRS | 1 | days | done | 2016-04-02 | 2016-04-03 | 2016-04-03 | 2016-04-04 | 1 | hrs | 1 | hrs | 100% |  | Yasser
4.2 | Update HLD | 1 | days | done | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 1 | hrs | 1 | hrs | 100% |  | Hassan
4.3 | Update CDDs | 2 | days | done | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-08 | 2 | hrs | 2 | hrs | 100% |  | Hoda
4.4 | Update Test cases | 2 | days | done | 2016-04-03 | 2016-04-03 | 2016-04-05 | 2016-04-08 | 2 | hrs | 2 | hrs | 100% |  | Mariam
4.5 | Update RTM | 1 | days | done | 2016-04-04 | 2016-04-04 | 2016-04-05 | 2016-04-08 | 1 | hrs | 1 | hrs | 100% | 4.1, 4.3, 4.4 | Kareem
4.6 | Function test | 2 | days | done | 2016-04-02 | 2016-04-07 | 2016-04-08 | 2016-04-08 | 4 | hrs | 4 | hrs | 100% | 4.4 | All Team
4.7 | Component test | 2 | days | done | 2016-04-02 | 2016-04-07 | 2016-04-08 | 2016-04-08 | 4 | hrs | 4 | hrs | 100% | 4.6 | All Team
4.8 | Integration Test | 2 | days | done | 2016-04-02 | 2016-04-07 | 2016-04-08 | 2016-04-08 | 4 | hrs | 4 | hrs | 100% | 4.7 | All Team
4.9 | User Acceptance Test | 1 | days | current | 2016-04-09 | 2016-04-09 | 2016-04-09 | NA | 4 | hrs | 0 | hrs | 0% |  | All Team
Formulas:
Actual Finish = [Actual Finish, row above]
Actual Start = [Actual Finish, row above]
Expected Start = [Expected Finish, row above]
Note on B8: Task Name A field in which you may type or edit information about the task to be performed.
Note on C8: Duration in Days A type of field whose content is expressed as a duration of time that represents the total span of active working time for a task.
Note on E8: Baseline Start Date The original project plans start date used to track progress on a project. The baseline is a snapshot of the schedule at the time that the schedule has been formally approved.
Note on F8: Expected Start Date The date when an assigned resource is scheduled to begin working on a task.
Note on G8: Actual Start Date The date when an assigned resource actually begins working on a task.
Note on H8: Expected Finish Date The date when an assigned resource is scheduled to finish working on a task.
Note on I8: Actual Finish Date The date when an assigned resource actually finishes working on a task.
Note on J8: Estimate At Complete (EAC) The total amount of time scheduled on a task at its completion for all resources assigned to that task.
Note on L8: Actual Work The amount of work that has already been done by resources assigned to tasks.
Note on N8: % Complete The current status of a task, expressed as the percentage of the task's completion.
Note on O8: Predecessors Task IDs for tasks that must start or finish before another task can start of finish.
Note on P8: Resource Names The list of all resources assigned to a task.